## Plan Summary
Student | Anderson Edmond | Assign. | 4 |  | Date | 2024-11-10
Instructor | Andrew Clifton |  |  |  | Course | CS 133
Final |  | Estimate |  | Actual
LOC/Hour |  | 0.14583 |  | 0.36349
Program Size (LOC) |  | Estimate |  | Actual
Created |  | 100 |  | 229
|  | (estimated) |  | (counted)
Δ Lines |  | 30 |  | 54
|  | (estimated) |  | (counted)
Final LOC |  | 70 |  | 229
(counted)
Time in Phase (min) |  | Estimate |  | Actual
Planning |  | 60 |  | 105
Design |  | 60 |  | 70
Code |  | 240 |  | 325
Compile |  | 0 |  | 20
Test |  | 60 |  | 110
Postmortem |  | 60
TOTAL |  | 480 |  | 630
Defects injected |  | Estimate |  | Actual
Planning |  | 6 |  | 0
Design |  | 2 |  | 1
Code |  | 5 |  | 8
Compile |  | 0 |  | 0
Test |  | 0 |  | 0
TOTAL |  | 13 |  | 9
Defects removed |  | Estimate |  | Actual
Planning |  | 2 |  | 0
Design |  | 1 |  | 2
Code |  | 8 |  | 3
Compile |  | 0 |  | 0
Test |  | 0 |  | 1
TOTAL development |  | 11 |  | 6
Post-development |  | 2 |  | 0

## Time log
Student | [5 empty] | Date
Instructor | Andrew Clifton |  |  |  |  | Course | CS 133
Date | Phase | Start time | Int. mins. | End time | Total | Comments
2024-11-12 | Plan | 11:00 |  | 12:15 | 1800:00 | Looked at videos on youtube |  | Totals per phase | Minutes
2024-11-22 | Code | 18:30 |  | 19:30 | 1440:00 | Attempted rotate function |  | Plan | 105
2024-11-22 | Design | 19:30 |  | 19:50 | 480:00 | Fixing node left/right issue |  | Design | 70
2024-11-22 | Code | 19:50 |  | 20:30 | 960:00 | Figuring out height adjustment |  | Code | 325
2024-11-22 | Compile | 20:30 |  | 20:50 | 480:00 | Was compiling .hpp file lol |  | Compile | 20
2024-11-23 | Design | 14:10 |  | 14:40 | 720:00 | Insert Function |  | Test | 110
2024-11-23 | Code | 14:40 |  | 16:00 | 1920:00 | Insert Function
2024-11-23 | Design | 20:30 |  | 20:50 | 480:00 | Height balance section of insert
2024-11-23 | Code | 20:50 |  | 21:15 | 600:00 | Height balance and rotate action
2024-11-23 | Test | 21:15 |  | 21:50 | 840:00 | duplicates error
2024-11-24 | Code | 11:30 |  | 12:00 | 720:00 | Destroy function
2024-11-24 | Code | 12:45 |  | 13:30 | 1080:00 | remaining functions attempt
2024-11-24 | Test | 13:30 |  | 14:45 | 1800:00 | Troubleshooting recursive find
2024-11-24 | Plan | 19:30 |  | 20:00 | 720:00 | Remaining functions
2024-11-24 | Code | 20:00 |  | 20:45 | 1080:00 | Size and copy function
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00

## Defect log
| Student | Anderson Edmond | [5 empty] | Date | 2024-11-10
| Instructor | Andrew Clifton | [5 empty] | Course | CS 133
Types
# | Inject | Remove | Type | Fix time (min) | ΔL | Fix ref. | Description |  |  | Docs | Documentation
1 | Code | Design | Logic | 20 | 7 |  | fixed missing node references |  |  | Syntax | Syntax, typo, punctuation
2 | Code | Code | Logic | 30 | 11 |  | adjusted condition checks |  |  | Build | Compilation and linking
3 | Code | Code | Syntax | 5 | 4 |  | height in rotate function |  |  | Variable | Naming, assignment, type
4 | Design | Code | Logic | 5 | 1 |  | parent variable for height balance |  |  | Interface | Public members/methods, function sig.
5 | Code | Test | Logc | 15 | 2 |  | infinite loop and incorrect rotate var |  |  | Checking | Checking assumptions
6 | Code | Design | Logic | 20 | 3 |  | duplicates check outside traversal |  |  | Data | Data structures, values
7 | Code | Testing | logic | 10 | 8 |  | nullptr check and needless pointer adj |  |  | Logic | Loops, conditions, pointers, recursion
8 | Code | Testing | Logic | 30 | 12 |  | all logic moved to find(node*n, x) |  |  | System | IO, timing, OS interaction
9 | Code | Testing | Logic | 30 | 6 |  | pointer assignment in copy function |  |  | Env | Editor, version control, SSH
10
11 | [9 empty] | Injects by phase
12 | [9 empty] | Plan | 0
13 | [9 empty] | Design | 1
14 | [9 empty] | Code | 8
15 | [9 empty] | Compile | 0
16 | [9 empty] | Test | 0
17
18 | [9 empty] | Removal by phase
19 | [9 empty] | Plan | 0
20 | [9 empty] | Design | 2
21 | [9 empty] | Code | 3
22 | [9 empty] | Compile | 0
23 | [9 empty] | Test | 1
24
25 | [9 empty] | Defects by type
26 | [9 empty] | Docs | 0
27 | [9 empty] | Syntax | 1
28 | [9 empty] | Build | 0
29 | [9 empty] | Variable | 0
30 | [9 empty] | Interface | 0
31 | [9 empty] | Checking | 0
32 | [9 empty] | Data | 0
33 | [9 empty] | Logic | 7
34 | [9 empty] | System | 0
35 | [9 empty] | Env | 0
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100